## Gantt
Boards - Maison (by weeks)
|  |  | Sep-2022 | Sep-2022 | Sep-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Oct-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Nov-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Dec-2022 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023 | Jan-2023
| Start | End | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Maison De Versa |  |  | 28: Maison De Versa
Ice Breaker | 28-Sep-2022 | 28-Sep-2022 | 28: Ice Breaker (28-Sep-22 - 28-Sep-22)
Setting up communication | 28-Sep-2022 | 28-Sep-2022 | 28: Setting up communication (28-Sep-22 - 28-Sep-22)
Belbin Boards | 05-Oct-2022 | 05-Oct-2022 | 5: Belbin Boards (05-Oct-22 - 05-Oct-22)
Milestone - Roles decided | 05-Oct-2022 | 05-Oct-2022 | 5: Milestone - Roles decided (05-Oct-22 - 05-Oct-22)
Exersize - Functional Requirement Analysis | 12-Oct-2022 | 12-Oct-2022 | 12: Exersize - Functional Requirement Analysis (12-Oct-22 - 12-Oct-22)
Exersize - Non-functional Requirements task | 12-Oct-2022 | 12-Oct-2022 | 12: Exersize - Non-functional Requirements task (12-Oct-22 - 12-Oct-22)
Choosing website name and niche | 12-Oct-2022 | 12-Oct-2022 | 12: Choosing website name and niche (12-Oct-22 - 12-Oct-22)
Creating Trello MoSCoW board | 12-Oct-2022 | 12-Oct-2022 | 12: Creating Trello MoSCoW board (12-Oct-22 - 12-Oct-22)
Exersize- Use Case examples | 13-Oct-2022 | 13-Oct-2022 | 13: Exersize- Use Case examples (13-Oct-22 - 13-Oct-22)
Creating Trello Tasks board | 13-Oct-2022 | 13-Oct-2022 | 13: Creating Trello Tasks board (13-Oct-22 - 13-Oct-22)
Making a github repository | 19-Oct-2022 | 19-Oct-2022 | 19: Making a github repository (19-Oct-22 - 19-Oct-22)
Figma Design for Maison De Versa | 23-Oct-2022 | 23-Oct-2022 | 23: Figma Design for Maison De Versa (23-Oct-22 - 23-Oct-22)
Git-branching task | 26-Oct-2022 | 26-Oct-2022 | 26: Git-branching task (26-Oct-22 - 26-Oct-22)
Assessment 1 Submission - Non-funtional and Functional Requirments | 27-Oct-2022 | 27-Oct-2022 | 27: Assessment 1 Submission - Non-funtional and Functional Requirments (27-Oct-22 - 27-Oct-22)
Brand Guidlines and Design Specification | 28-Oct-2022 | 28-Oct-2022 | 28: Brand Guidlines and Design Specification (28-Oct-22 - 28-Oct-22)
Assessment 1 Submission - Functional Requirements | 29-Oct-2022 | 29-Oct-2022 | 29: Assessment 1 Submission - Functional Requirements (29-Oct-22 - 29-Oct-22)
Assessment 1 - Use cases and Technology used section | 30-Oct-2022 | 30-Oct-2022 | 30: Assessment 1 - Use cases and Technology used section (30-Oct-22 - 30-Oct-22)
Creating Gantt Chart | 31-Oct-2022 | 31-Oct-2022 | 31: Creating Gantt Chart (31-Oct-22 - 31-Oct-22)
Setting up Azure for hosting | 04-Nov-2022 | 04-Nov-2022 | 4: Setting up Azure for hosting (04-Nov-22 - 04-Nov-22)
Submitting System Requirements | 04-Nov-2022 | 04-Nov-2022 | 4: Submitting System Requirements (04-Nov-22 - 04-Nov-22)
Submitting Designed Alliance | 04-Nov-2022 | 04-Nov-2022 | 4: Submitting Designed Alliance (04-Nov-22 - 04-Nov-22)
Submitting Independant report | 04-Nov-2022 | 04-Nov-2022 | 4: Submitting Independant report (04-Nov-22 - 04-Nov-22)
Homepage HTML | 10-Nov-2022 | 10-Nov-2022 | 10: Homepage HTML (10-Nov-22 - 10-Nov-22)
Homepage/index CSS | 10-Nov-2022 | 10-Nov-2022 | 10: Homepage/index CSS (10-Nov-22 - 10-Nov-22)
Logo added to homepage + Adding images to Homepage | 16-Nov-2022 | 16-Nov-2022 | 16: Logo added to homepage + Adding images to Homepage (16-Nov-22 - 16-Nov-22)
Working Basket System | 17-Nov-2022 | 17-Nov-2022 | 17: Working Basket System (17-Nov-22 - 17-Nov-22)
Session Logout PHP | 23-Nov-2022 | 23-Nov-2022 | 23: Session Logout PHP (23-Nov-22 - 23-Nov-22)
Receive Detailed Submission 1 Feedback | 23-Nov-2022 | 23-Nov-2022 | 23: Receive Detailed Submission 1 Feedback (23-Nov-22 - 23-Nov-22)
Checkout System for Website | 28-Nov-2022 | 28-Nov-2022 | 28: Checkout System for Website (28-Nov-22 - 28-Nov-22)
Log in/Register page design | 29-Nov-2022 | 29-Nov-2022 | 29: Log in/Register page design (29-Nov-22 - 29-Nov-22)
Product page | 29-Nov-2022 | 29-Nov-2022 | 29: Product page (29-Nov-22 - 29-Nov-22)
Shop page frontend | 29-Nov-2022 | 29-Nov-2022 | 29: Shop page frontend (29-Nov-22 - 29-Nov-22)
Design for basket updated | 29-Nov-2022 | 29-Nov-2022 | 29: Design for basket updated (29-Nov-22 - 29-Nov-22)
About page design/frontend | 30-Nov-2022 | 30-Nov-2022 | 30: About page design/frontend (30-Nov-22 - 30-Nov-22)
login page design | 30-Nov-2022 | 30-Nov-2022 | 30: login page design (30-Nov-22 - 30-Nov-22)
Pushing completed documents and files to Github | 01-Dec-2022 | 01-Dec-2022 | 1: Pushing completed documents and files to Github (01-Dec-22 - 01-Dec-22)